## PM Invoice Prep Checklist
Department of General Services
Capital Construction Services
Invoice Processing Checklist
Responsibility of the Project Manager
1 | Vendor's Invoice Accuracy Review
a. All appropriate documents are attached to include:
- CIP form (Is per item price list attached for FFE)
- Progress Payment Request Form (Page 1)
- Progress Payment Request Form Schedule of Values (Page 2)
- Release of Lien for GC or Proof of Payment Affidavit for AE (Not required if invoice is for equipment and/or support services)
- Retainage reduction letter signed by the Cluster Leader is required when reducing retainage
- CBE form
b. Make sure all documents reflect the amount billed for payment.
c. Make sure the billing period is within the contract period.
d. Make sure the original contract value is reflected on line 1 of the payment request form.
e. Project Manager signature must include date signed.
2 | Prolog Invoice entry
a. The invoice date must match the ACTUAL VENDOR'S INVOICE date. (AIA invoice dates are per VENDOR'S signature date)
b. The "Period" in the prolog invoice must match the ending date of the vendor's billing period.
c. The "Itemized Breakdown" tab must reflect the vendor's invoice amount in the "Net Current Due".
d. The "Financial Summary" tab must reflect the vendor's invoice amount in the "Current Payment Due".
e. The date the invoice was received by the PM is entered into the "Other Information" tab and should match the vendor's signature date.
f. The invoice approval date on the "Other Information" tab must be left blank. This date will match the Deputy Director's Approval date and is entered by the PMO team.
g. The Vendor's Invoice Number from the vendor's invoice is entered onto the "Other information" tab. (AIA documents - PO Number & Pay App Number)
g. The Invoice Status must be set to Pending. PMO team will change once approved by the Deputy Director.
h. Enter the billing period start and end date on "Additional Information"
i. Attach Certified Payrolls to the "Files" tab. (Naming Nomenclature as follows: Vendor Name_PO8888888_Inv Number_Invoice Amt $1,000,000_Cert Pay)
3 | After the invoice has been signed and dated by the PM and entered into prolog it will be saved on the U:\ drive (Naming Nomenclature as follows: Agency-Sequence-Type_Vendor Name_PO888888_Vendor Invoice Number_Invoice Amount $1,000)
4 | Cluster leader will review the invoice, sign, date and save it in the "PMO Review Folder" on the U:\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review)
Updated date: 4/24/2015