## Contract Review Checklist (hidden)
Department of General Services
Capital Construction Services
Contract Review Checklist
For the PMO Team
1 | Purchase Order from PASS
Notes:
2 | Executed Contract
Notes:
3 | NTP (Notice to Proceed)
Notes:
4 | Do the dates on the "Detailed Information's" tab match the NTP?
Notes:
5 | Contract Amounts (Schedule of Values)
Notes:
6 | Does the "Contract Amounts" tab match what's on the contract documents?
Notes:
7 | Period of Performance
Notes:
8 | Does the POP match the dates shown to the "Detailed Information's" tab (S/C & End Date)?
Notes:
9 | If the POP is not specified in the contract document based on delivery of equipment or furniture, a signed schedule from your cluster leader is required.
Notes:
10 | Subcontracting Plan (contracts/PO's in the amount of $250k and over)
Notes:
11 | Are all documents attached in Prolog?
Notes:
Updated date: 4/24/2015

## Contract documents for review (hidden)
Department of General Services
Capital Construction Services
Contract Document Checklist
For the Project Manager
1 | Purchase Order from PASS
2 | Executed Contract
3 | NTP (Notice to Proceed)
4 | Do the dates on the "Detailed Information's" tab match the NTP?
5 | Contract Amounts (Schedule of Values)
6 | Does the "Contract Amounts" tab match what's on the contract documents?
7 | Period of Performance
8 | Does the POP match the dates shown on the "Detailed Information's" tab (S/C & End Date)?
9 | If the POP is not specified in the contract document based on delivery of equipment or furniture, a signed schedule from your cluster leader is required.
10 | Subcontracting Plan (contracts/PO's in the amount of $250k and over)
11 | Are all documents attached in Prolog?
Updated date: 4/24/2015

## PMO Invoice Review Checklist (hidden)
Department of General Services
Capital Construction Services
Invoice Processing Checklist
Responsibility of the PMO Team
1 | Vendor's Invoice Accuracy Review
a. All appropriate documents are attached to include:
- CIP form (Is per item price list attached for FFE)
- Progress Payment Request Form (Page 1)
- Progress Payment Request Form Schedule of Values (Page 2)
- Release of Lien for GC or Proof of Payment Affidavit for AE (Not required if invoice is for equipment and/or support services)
- Retainage reduction letter signed by the Cluster Leader is required when reducing retainage
- CBE form
b. Make sure all documents reflect the amount billed for payment.
c. Make sure the billing period is within the contract period.
d. Make sure the original contract value is reflected on line 1 of the payment request form.
e. Project Manager signature must include date signed.
2 | Prolog Invoice entry
a. Does the invoice date match the ACTUAL VENDOR'S INVOICE date? (AIA invoice dates are per VENDOR'S signature date)
b. Does the "Period" in the prolog invoice match the ending date of the vendor's billing period?
c. Does the "Itemized Breakdown" tab reflect the vendor's invoice amount in the "Net Current Due"?
d. Does the "Financial Summary" tab reflect the vendor's invoice amount in the "Current Payment Due".
e. Has the date the invoice was received by the PM been entered into the "Other Information" tab and does it match the vendor's signature date?
f. Enter the invoice approval date on the "Other Information" tab. This date will match the Deputy Director's Approval date.
g. Has the Vendor's Invoice Number from the vendor's invoice been entered onto the "Other information" tab? (AIA documents - PO Number & Pay App Number)
g. Has the Invoice Status been set to Pending?
h. Has the billing period start and end date been entered onto the "Additional Information" tab?
i. Are Certified Payrolls uploaded into the "Files" tab. (Naming Nomenclature as follows: Vendor Name_PO8888888_Inv Number_Invoice Amt $1,000,000_Cert Pay)
3 | Invoice Processing for Deputy Director's signature
a. After receiving the document from the Cluster leader in the "PMO Review Folder" on the U:\\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review)....print and follow steps 1 and 2 above to review the invoice in preparation for the Deputy Director's signature.
b. Once Deputy Director has signed the invoices; scan to a flash drive then save them to the U:\\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review\PRINT_SIGN)
c. Diane and Edwina will complete receiving of these documents in PASS and the PM will approve the receipt.
d. Once receiving has been completed in PASS invoices will be added to the Sent to DGS Finance Log and forwarded to Finance.
Updated date: 4/24/2015

## PM Invoice Prep Checklist (hidden)
Department of General Services
Capital Construction Services
Invoice Processing Checklist
Responsibility of the Project Manager
1 | Vendor's Invoice Accuracy Review
a. All appropriate documents are attached to include:
- CIP form (Is per item price list attached for FFE)
- Progress Payment Request Form (Page 1)
- Progress Payment Request Form Schedule of Values (Page 2)
- Release of Lien for GC or Proof of Payment Affidavit for AE (Not required if invoice is for equipment and/or support services)
- Retainage reduction letter signed by the Cluster Leader is required when reducing retainage
- CBE form
b. Make sure all documents reflect the amount billed for payment.
c. Make sure the billing period is within the contract period.
d. Make sure the original contract value is reflected on line 1 of the payment request form.
e. Project Manager signature must include date signed.
2 | Prolog Invoice entry
a. The invoice date must match the ACTUAL VENDOR'S INVOICE date. (AIA invoice dates are per VENDOR'S signature date)
b. The "Period" in the prolog invoice must match the ending date of the vendor's billing period.
c. The "Itemized Breakdown" tab must reflect the vendor's invoice amount in the "Net Current Due".
d. The "Financial Summary" tab must reflect the vendor's invoice amount in the "Current Payment Due".
e. The date the invoice was received by the PM is entered into the "Other Information" tab and should match the vendor's signature date.
f. The invoice approval date on the "Other Information" tab must be left blank. This date will match the Deputy Director's Approval date and is entered by the PMO team.
g. The Vendor's Invoice Number from the vendor's invoice is entered onto the "Other information" tab. (AIA documents - PO Number & Pay App Number)
g. The Invoice Status must be set to Pending. PMO team will change once approved by the Deputy Director.
h. Enter the billing period start and end date on "Additional Information"
i. Attach Certified Payrolls to the "Files" tab. (Naming Nomenclature as follows: Vendor Name_PO8888888_Inv Number_Invoice Amt $1,000,000_Cert Pay)
3 | After the invoice has been signed and dated by the PM and entered into prolog it will be saved on the U:\ drive (Naming Nomenclature as follows: Agency-Sequence-Type_Vendor Name_PO888888_Vendor Invoice Number_Invoice Amount $1,000)
4 | Cluster leader will review the invoice, sign, date and save it in the "PMO Review Folder" on the U:\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review)
Updated date: 4/24/2015

## Invoice Revew Checklist
Department of General Services
Capital Construction Services
Invoice Processing Checklist
Step | Description | PMO | PM
1 | Prolog Invoice Entry - PMO (will do) & PM (will review and edit if necessary) E-mail notification from Prolog will be sent to the PM and Cluster Leader that invoice has been "shelled"
2 | Vendor's Invoice Accuracy Review - PM & PMO
a. All appropriate documents are attached to include:
- CIP form (Is per item price list attached for FFE)
- DGS Pay Request Form (Page 1)
- DGS Pay Request Form Schedule of Values (Page 2)
- Release of Lien for GC (Not required if invoice is for equipment and/or support services)
- Retainage reduction letter signed by the Cluster Leader is required when reducing retainage
- CBE form
b. Make sure all documents reflect the exact same amount due for payment. (Vendor invoice on letterhead - DGS Pay Request form and AIA document if included)
c. Make sure the billing period is within the contract period.
d. Make sure the original contract value is reflected on line 1 of the payment request form.
e. Project Manager signature and date signed.must be included
3 | Prolog Invoice Entry - PMO (will do) & PM (will review and edit if necessary)
a. Invoice date on Pay Request form should match the actual vendor's invoice or AIA invoice dates
b. Does the "Period" in the Prolog invoice match the ending date of the vendor's billing period?
c. Does the "Itemized Breakdown" tab in Prolog reflect the vendor's invoice amount in the "Net Current Due"?
d. Does the "Financial Summary" tab in Prolog reflect the vendor's invoice amount in the "Current Payment Due".
e. Enter the invoice approval date on the "Other Information" tab. This date will match the Deputy Director's Approval date.
f. Enter/Review the Vendor's Invoice Number from the vendor's invoice on the "Other information" tab? (AIA documents - PO Number & Pay App Number)
g. Change the invoice status to Pending?
h. Enter/Review the billing period start and end date been entered onto the "Additional Information" tab?
i. Make sure the Prolog billing period number correspondes to the correct billing period on the invoice
j. Check to make sure that Certified Payroll has uploaded into the "Files" tab. (Naming Nomenclature as follows: Vendor Name_PO8888888_Inv Number_Invoice Amt $1,000,000_Cert Pay)
4 | After the Prolog invoice data has been reviewed and if necessary edited the PM will sign and place the entire signed invoice packet into the appropriate Cluster Leaders folder on the U drive. (Naming Nomenclature as follows: Vendor Name_PO888888_Vendor Invoice Number_Invoice Amount $1,000).
5 | Cluster leader will review the invoice, sign, date and save it in the "PMO Review Folder" on the U:\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review)
a. After review and signing the Cluster leader will put the signed invoice packet in the "PMO Review Folder" on the U:\\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review
b. PMO staff will print and review the entire invoice packet and if erroneous or incomplete the status in Prolog will be changed to "Rejected" and the Additional Information tab will be updated to include the reason(s) for the rejecttion
c. If the packet is correct and complete it will route for signature from Deputy Director / Chief Project Delivery Officer / Contracting Officer (invoices > $1M)
6 | Invoice review and approval: Deputy Director / Chief Project Delivery Officer / Contracts & Procurement (invoices > $1M)
a. Once the invoice is fully approved PMO staff will scan to a flash drive then save them to the U:\\ drive (\\DGSSHARE01\Capital-Construction\opmfile\ccsa\_Invoice Processing\_PMO Review\PRINT_SIGN for the appropriate day)
b. PMO will do receiving in PASS and attach fully approved copies of the invoices to the appropriate receipt in PASS.
c. Report sent to DGS Finance/OCFO of all invoices that have been received in PASS and are ready for payment processing.
Updated date: 12/19/17