Janney ES Addition: May 6, 2014

Project Update

Update of April Site Activities

* Spring Break:
	+ Tompkins mobilized for the entire week of spring break (April 12th - April 21st )
	+ Bar Joists & metal decking installation was completed on the 3rd floor level.
	+ Structural Steel installation was completed on the 3rd floor and roof levels.
	+ Light gage metal framing installation was completed on the 3rd floor.
	+ Roofing was installed along with sheathing and Blueskin
	+ Mechanical and Electrical rough-in began
	+ Existing IT rooms were cleaned
	+ Ductwork on the gymnasium were redirected through the roof
	+ Relocation of the Rooftop Mechanical Units was Complete
* April Weekends:
	+ The remainder of the structural steel was erected for the 3rd floors
	+ The remainder of the light gage metal framing was installed for the 3rd floor
	+ Joists and metal deck were installed on the 3rd floor and roof levels.

Look Ahead:

* + Continuation of Mechanical and Electrical Rough-in
	+ Installation of exterior metal panel and storefront windows
	+ Begin pouring concrete on west half of addition above structural steel
	+ Begin installing interior wall partitions and door frames
	+ Achieve a water-tight shell to begin interior installation and fit-out