Janney ES Addition: May 6, 2014

Project Update

Update of April Site Activities

* Spring Break:
  + Tompkins mobilized for the entire week of spring break (April 12th - April 21st )
  + Bar Joists & metal decking installation was completed on the 3rd floor level.
  + Structural Steel installation was completed on the 3rd floor and roof levels.
  + Light gage metal framing installation was completed on the 3rd floor.
  + Roofing was installed along with sheathing and Blueskin
  + Mechanical and Electrical rough-in began
  + Existing IT rooms were cleaned
  + Ductwork on the gymnasium were redirected through the roof
  + Relocation of the Rooftop Mechanical Units was Complete
* April Weekends:
  + The remainder of the structural steel was erected for the 3rd floors
  + The remainder of the light gage metal framing was installed for the 3rd floor
  + Joists and metal deck were installed on the 3rd floor and roof levels.

Look Ahead:

* + Continuation of Mechanical and Electrical Rough-in
  + Installation of exterior metal panel and storefront windows
  + Begin pouring concrete on west half of addition above structural steel
  + Begin installing interior wall partitions and door frames
  + Achieve a water-tight shell to begin interior installation and fit-out