Janney ES Addition: January 7, 2014

Project Update

Update of Preparation Activities over the Holiday Break:

* Site Mobilization:
  + Mobilization of materials, tools & equipment
  + Establish construction zone and fencing
* Selective Demolition
  + Removal of existing roof screen. Materials to be reused on the addition.
* Structural Reinforcement
  + Added WT and C Channel members to existing I beams above the ceilings of the Pre K Classrooms.
  + Installed structural roof curbs that will receive the new light gage framed Partitions

Look Ahead:

* MLK Weekend – January 18-20
  + Complete prepatory work on roof
  + Erect Scaffold at future stair tower
* February 1-2
  + Erect Self Erecting Crane
  + Begin Masonry Tower
* Presidents Day – February 14-17
  + Erect 2nd floor light gage walls and structural steel