Janney ES Addition: March 3, 2014

Project Update

Update of February Site Activities

* President’s Day Weekend:
	+ Stair Tower CMU installation continued
	+ Major material deliveries for Steel and Light gage metal.
	+ Structural steel was erected at and above the gym entrance on the South side of the building
* Stair Tower Installation:
	+ Tompkins worked almost all weekend days in February on installing the CMU stair tower on the South end of the addition. The stair tower CMU is on the 3rd level and almost complete as of this report.
	+ Imbeds were received from the Metals contractor and incorporated into the Stair tower for future steel connections.
* Feb 22/23rd & March 1/2nd Weekends:
	+ Additional structural steel was erected for the 2nd floor.
	+ Light Gage wall panels were installed for the 2nd floor framing

Look Ahead:

* March Weekends:
	+ Tompkins plans to be on-site every weekend in March
	+ The CMU at the stair tower will be completed.
	+ The remainder of the structural steel will be erected for the 2nd and 3rd floors
	+ The remainder of the light gage metal framing will be installed for the 2nd floor
	+ Joists and Metal deck will arrive the last weekend of March and be installed, followed by the 3rd floor light gage metal framing.